## Pricing Matrix
MYCURE Corporate Clinic Ecosystem — Commercial Model Matrix
First 100 Clinics Lock-In Offer — Discounted Pricing Options (Indicative)
Category | Module / Item | Model 1 Perpetual License MediCard Hosting | Model 2 Corporate Service Plan MediCard Hosting | Model 3 Corporate Service Plan MYCURE Hosting | Notes / Assumptions
CORPORATE CLINIC CORE
Core Modules | Core Package (Corporate EMR + clinic ops) | ₱280,000 Promo lock-in Post-promo: ₱300,000 | ₱6,000 / clinic / month Promo lock-in Post-promo: ₱8,000 200 per day* just a note or Bulk Pricing 1 clinic - 12.5k 10 clinics - 20% off | ₱10,000 / clinic / month Promo lock-in Post-promo: ₱13,000 MYCURE Basic - 18,000 +add ons 25-30k | Current figures are first-100-clinic lock-in rates. Post-promo rates are shown in the same cells for quick comparison.
| Corporate EMR Includes extensive medical records, Exams & Certificates Hub, and Diagnostics Bridge | Included | Included | Included | One consolidated clinical record layer covering consult history, certificates, exam workflows, diagnostics results, and corporate clinic documentation.
| Attendance Management | Included | Included | Included | Clinic team attendance, logs, and operating visibility.
| Clinic Insights Dashboard | Included | Included | Included | Operational and clinical trend views for corporate clinic monitoring.
| Lock-in mechanics | First 100 clinics reserved at promo rate | First 100 clinics reserved at promo rate | First 100 clinics reserved at promo rate | Post-promo pricing applies to new clinics or commitments made after the offer expires.
OPTIONAL ADD-ON PACKS (per clinic)
Add-On | Workplace Health Compliance Pack | 80000 | 1800 | 1600 | OSH/DOLE documentation & reporting support
Add-On | Corporate & HR Health Insights Pack | 80000 | 1800 | 1600 | Privacy-conscious HR portal, FTW status, trends
Add-On | Pharmacy & Supplies Pack | 50000 | 1200 | 1000 | Stock tracking, expiry alerts, dispensing logs
Add-On | Syncbase |  |  |  | Integration/sync layer add-on; commercial rate to be finalized.
RECURRING FEES
Recurring | Annual Maintenance & Support (AMS) | 20% of license value per year | Included in managed service | Included in managed cloud service | Perpetual model: AMS billed separately. Managed service plans: updates, support, security included.
Recurring | Hosting / Infrastructure | MediCard's cost (own infra) | MediCard's cost (own infra) | Included in managed cloud service | Model 3: MYCURE absorbs hosting. Models 1 & 2: MediCard provisions servers.
IMPLEMENTATION & TRAINING
Services | Implementation Package (first 50 clinics) | 3000000 | 3000000 | 3500000 | Implementation fee covers the first 50 clinics, including pilot setup, onboarding, training, rollout support, and hypercare. Model 3 remains higher due to security review, DPA setup, and cloud migration scoping.
Services | Per Additional Clinic Onboarding | 50000 | 50000 | 35000 | Model 3 lower per-clinic onboarding since infra is pre-provisioned.

## Sheet1
Bulk | MediCard Hosting
1 clinic | 12500
10-49 clinics | 11250
50-99 | 9000
100-149 | 6750
150> | 5400
Optional Training

## Timeline Comparison
Implementation Timeline Comparison by Commercial Model
Models 1 & 2 can reach first pilot clinic go-live in ~3-4 weeks under a fast-track path: pilot authorization via LOA/SOW, MediCard hosting ready in Week 1, no custom development before pilot, and initial pilot scope limited to 1-3 clinics. Model 3 remains longer due to MYCURE-hosted security checks, VAPT, TPSA/vendor risk review, DPA/SLA, and cloud onboarding, but can be contained with parallel review workstreams.
Phase / Activity | Model 1 Perpetual MediCard Hosting | Model 2 Corporate Service Plan MediCard Hosting | Model 3 Corporate Service Plan MYCURE Hosting | Key Dependencies / Notes
CONTRACT & PROCUREMENT
Pilot SOW / LOA / commercial sign-off | 3-5 business days | 3-5 business days | 4-6 weeks | Models 1 & 2: use pilot authorization while long-form contract continues in parallel. Model 3 requires hosted-service legal/security clauses, but these can run alongside security review.
Security, VAPT, TPSA / vendor risk review | Deployment checklist only (app ready; MediCard hosts) | Deployment checklist only (app ready; MediCard hosts) | 4-6 weeks (security-gated) | Models 1 & 2 avoid full MYCURE-cloud review because MediCard hosts. Model 3 requires VAPT/TPSA/vendor risk review, but target a focused pilot approval path rather than enterprise-wide clearance upfront.
READINESS & ENABLEMENT
Hosting / environment readiness | 3-5 business days (MediCard ready by Week 1) | 3-5 business days (MediCard ready by Week 1) | 1-2 weeks (MYCURE provisions) | Fast-track requirement: MediCard provides server/cloud environment, database, network/VPN or Tailscale access, backups, and admin access within Week 1. Model 3 cloud setup can proceed in parallel after initial security alignment.
Training & operating model alignment | 3-5 business days (parallel) | 3-5 business days (parallel) | 1-2 weeks (parallel) | Train-the-trainer and role-based sessions run in parallel with setup, not after setup.
PILOT ROLLOUT
Program setup & platform configuration | 3-5 business days | 3-5 business days | 1-2 weeks | Models 1 & 2 use ready MYCURE baseline with no custom development before pilot. Model 3 uses the same baseline after hosted controls are approved.
First pilot clinic (1-3 sites) | Week 3-4 | Week 3-4 | Week 10-14 | Initial pilot scope is intentionally tight. Model 3 starts later, but can still avoid a long delay if VAPT/TPSA and DPA/SLA activities are run in parallel.
WAVE ROLLOUT
Subsequent clinic waves (batches of 10-20) | 2-3 weeks per wave | 2-3 weeks per wave | 2-3 weeks per wave | Per-clinic onboarding remains standardized once pilot workflow, training, and support paths are stable.
TOTAL ESTIMATED TIMELINE
Contract to first pilot clinic go-live | ~3-4 weeks (fast-track) | ~3-4 weeks (fast-track) | ~10-14 weeks | Models 1 & 2 require LOA/SOW, Week 1 hosting readiness, no custom development, and 1-3 clinic pilot scope. Model 3 remains longer, but targeted at ~10-14 weeks with parallel security/legal workstreams.
Contract to full 150-clinic rollout completion | ~5-9 months | ~5-9 months | ~8-12 months | Fast-track first pilot can pull the front end forward. Model 3 remains longer due to hosted-security approval, but not proportionally delayed once the cloud service is cleared.

## 5-Year TCO
5-Year Total Cost of Ownership (TCO) — Per Clinic (Core Only)
Indicative figures using first-100-clinic lock-in rates. Excludes add-on packs, implementation, and hosting infra costs for Models 1 & 2.
Cost Component | Model 1 Perpetual MediCard Hosting | Model 2 Corporate Service Plan MediCard Hosting | Model 3 Corporate Service Plan MYCURE Hosting | Notes
ASSUMPTIONS
Core license (one-time promo) | 280000 | N/A | N/A | Discounted lock-in rate; post-promo list rate is ₱300,000
Managed service fee (monthly promo) | N/A | 12000 | 10000 | Discounted lock-in rates; post-promo list rates are ₱15,000 and ₱13,000 per clinic/month
5-YEAR COST BREAKDOWN (per clinic, Core only)
Year 1 | 336000 | 144000 | 120000
Year 2 | 56000 | 144000 | 120000 | M1: AMS only. M2/M3: 12 months managed service.
Year 3 | 56000 | 144000 | 120000
Year 4 | 56000 | 144000 | 120000
Year 5 | 56000 | 144000 | 120000
5-YEAR TOTAL (per clinic) | ₱560,000 | ₱720,000 | ₱600,000
Effective monthly cost (over 60 months) | ₱9,333 | ₱12,000 | ₱10,000 | Amortized monthly for comparison only. Does not include hosting infra for M1/M2.

## Model Comparison
Commercial Model Comparison — Quick Reference
Dimension | Model 1 Perpetual License MediCard Hosting | Model 2 Corporate Service Plan MediCard Hosting | Model 3 Corporate Service Plan MYCURE Hosting
Upfront investment | Highest (full license + implementation) | Low (implementation only) | Low (implementation only, slightly higher due to security/migration)
Monthly cash outflow | None (AMS billed annually) | Predictable managed service fee (₱12,000/clinic) | Predictable managed cloud service fee (₱10,000/clinic)
5-Year TCO (Core only, per clinic) | Middle before MediCard hosting infra | Highest before MediCard hosting infra | High, with MYCURE hosting included
Hosting responsibility | MediCard IT (servers, backups, uptime) | MediCard IT (servers, backups, uptime) | MYCURE (fully managed cloud)
Data residency | MediCard-controlled (on-prem or own cloud) | MediCard-controlled (on-prem or own cloud) | MYCURE cloud (PH-based, subject to DPA and SLA)
Security review effort for MediCard | Light (app ready; internal path) | Light (app ready; internal path) | Moderate-Extended (VAPT, TPSA, DPA/SLA, cloud review)
Time to first pilot go-live | ~3-4 weeks (fast-track) | ~3-4 weeks (fast-track) | ~10-14 weeks (hosted-security path)
Scalability (adding clinics) | Requires MediCard to provision infra per batch | Requires MediCard to provision infra per batch | Elastic — MYCURE scales cloud resources on demand
Software ownership after contract ends | MediCard retains perpetual license (last version at exit) | Managed access ends when service stops | Managed access ends when service stops
Best fit for | MediCard prefers full ownership & control of data/infra | MediCard wants predictable OPEX but controls infra | MediCard wants lowest upfront + fully managed service
Risk to MYCURE | Revenue front-loaded; relies on AMS renewals | Predictable recurring; churn risk | Highest recurring; hosting cost exposure; strongest lock-in
Risk to MediCard | Capex-heavy; infra maintenance burden | Infra maintenance burden remains; managed-service lock-in | Vendor dependency; data residency concerns; security-gated onboarding